# EXPERIMENT 5

## WORK BREAKDOWN STRUCTURE (WBS)

## AND

## RISK MANAGEMENT

## SRM University Cybersecurity Moonshot Initiative

Prepared by: Moonshot Council

Date: January 19, 2026

# Executive Summary

The SRM Cybersecurity Moonshot Initiative is a 6-year transformation program with a total investment of ₹75 crores. This document provides the Work Breakdown Structure (WBS) detailing all project activities, milestones, and schedules, along with a comprehensive Risk Management plan.

**Key Milestones:**
• Year 1 (Foundation): CISO appointment, security audit, policy framework, MFA deployment
• Year 2-3 (Infrastructure): SOC establishment, SIEM deployment, Zero Trust implementation
• Year 3-4 (Education): B.Tech launch, research center establishment, 20+ faculty hiring
• Year 4-5 (Ecosystem): 20+ industry partnerships, CERT-In collaboration established
• Year 5-6 (Maturity): ISO 27001 certification, 500+ graduates, self-sustaining operations

**Critical Target Dates:**
• Month 3: CISO Appointment
• Month 6: Security Audit Completion
• Month 12: MFA Deployment Complete (70,000+ users)
• Month 18: SOC Operational (24x7)
• Month 24: B.Tech Program Launch (First 60 students)
• Month 36: Research Center Operational
• Month 48: ISO 27001 Certification
• Month 72: Program Maturity & Self-Sustainability

**Project Schedule Overview:**
The project is divided into 5 major phases spanning 72 months, with 25+ major modules, 150+ activities, and 500+ sub-tasks. Team assignments follow RACI matrix principles with clear accountability for deliverables.

**Risk Management Approach:**
Comprehensive risk identification through SWOT analysis, stakeholder brainstorming, and lessons learned from similar initiatives. Identified 35 major risks across 8 categories, with mitigation strategies and contingency plans for high-impact risks.

# Work Breakdown Structure (WBS) with Project Schedule

Team members assigned for sub-tasks based on RACI (Responsible, Accountable, Consulted, Informed) matrix and skill requirements.

## Phase 1: Foundation (Year 1) - ₹12 Crores

| Module (#) | Activity (#) | Sub-Task (#) | Assignee(s) | Start Date | End Date | Duration | Dependencies | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M1.1 Leadership | A1.1.1 CISO Recruitment | T1.1.1.1 Job posting | HR Team | M1 | M2 | 1 month | - | Planned |
|  |  | T1.1.1.2 Interviews | Hiring Committee | M2 | M3 | 1 month | T1.1.1.1 | Planned |
|  |  | T1.1.1.3 Onboarding | HR Team | M3 | M4 | 1 month | T1.1.1.2 | Planned |
|  | A1.1.2 Moonshot Council | T1.1.2.1 Council formation | Vice Chancellor | M1 | M2 | 1 month | - | Planned |
|  |  | T1.1.2.2 First meeting | CISO | M3 | M3 | 2 weeks | T1.1.1.3 | Planned |
| M1.2 Assessment | A1.2.1 Security Audit | T1.2.1.1 Vendor selection | CISO | M3 | M4 | 1 month | T1.1.1.3 | Planned |
|  |  | T1.2.1.2 Audit execution | Audit Team | M4 | M6 | 2 months | T1.2.1.1 | Planned |
|  |  | T1.2.1.3 Report & recommendations | Audit Lead | M6 | M7 | 1 month | T1.2.1.2 | Planned |
|  | A1.2.2 Risk Assessment | T1.2.2.1 Risk identification | Security Team | M4 | M5 | 1 month | T1.2.1.1 | Planned |
|  |  | T1.2.2.2 Risk analysis | Risk Manager | M5 | M6 | 1 month | T1.2.2.1 | Planned |
| M1.3 Policy | A1.3.1 Policy Framework | T1.3.1.1 Policy drafting | Policy Team | M5 | M7 | 2 months | T1.2.1.3 | Planned |
|  |  | T1.3.1.2 Stakeholder review | All Deans | M7 | M8 | 1 month | T1.3.1.1 | Planned |
|  |  | T1.3.1.3 Approval | Moonshot Council | M8 | M9 | 1 month | T1.3.1.2 | Planned |
| M1.4 Quick Wins | A1.4.1 MFA Deployment | T1.4.1.1 Solution selection | IAM Team | M6 | M7 | 1 month | T1.2.1.3 | Planned |
|  |  | T1.4.1.2 Pilot (1000 users) | IAM Team | M7 | M8 | 1 month | T1.4.1.1 | Planned |
|  |  | T1.4.1.3 Full rollout (70K) | IAM Team | M8 | M12 | 4 months | T1.4.1.2 | Planned |
|  | A1.4.2 Phishing Training | T1.4.2.1 Platform setup | Training Team | M7 | M8 | 1 month | - | Planned |
|  |  | T1.4.2.2 First campaign | Training Team | M8 | M9 | 1 month | T1.4.2.1 | Planned |
|  | A1.4.3 Basic SIEM | T1.4.3.1 SIEM procurement | CISO | M8 | M10 | 2 months | - | Planned |
|  |  | T1.4.3.2 Deployment | SOC Team | M10 | M12 | 2 months | T1.4.3.1 | Planned |

## Phase 2: Infrastructure (Years 2-3) - ₹25 Crores

| Module | Activity | Sub-Task | Assignee | Start Date | End Date | Duration | Dependencies | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M2.1 SOC Setup | A2.1.1 Facility | T2.1.1.1 Space preparation | Facilities Team | M13 | M15 | 2 months | - | Planned |
|  |  | T2.1.1.2 Equipment install | IT Team | M15 | M18 | 3 months | T2.1.1.1 | Planned |
|  | A2.1.2 SOC Staffing | T2.1.2.1 Analyst hiring (15) | HR Team | M13 | M18 | 5 months | - | Planned |
|  |  | T2.1.2.2 Training program | SOC Manager | M16 | M18 | 2 months | T2.1.2.1 | Planned |
|  | A2.1.3 SOC Operations | T2.1.3.1 24x7 ops start | SOC Manager | M18 | M18 | 1 week | T2.1.1.2 | Planned |
| M2.2 SIEM | A2.2.1 Advanced SIEM | T2.2.1.1 Log source integration | SIEM Admin | M13 | M18 | 5 months | - | Planned |
|  |  | T2.2.1.2 Correlation rules | SOC Analysts | M16 | M24 | 8 months | T2.2.1.1 | Planned |
|  |  | T2.2.1.3 Threat intel feeds | Threat Analyst | M18 | M20 | 2 months | T2.2.1.1 | Planned |
| M2.3 Zero Trust | A2.3.1 Architecture | T2.3.1.1 Design | Security Architect | M15 | M18 | 3 months | - | Planned |
|  |  | T2.3.1.2 Phase 1 impl | Network Team | M18 | M30 | 12 months | T2.3.1.1 | Planned |
|  |  | T2.3.1.3 Phase 2 impl | Network Team | M30 | M48 | 18 months | T2.3.1.2 | Planned |
| M2.4 Endpoint | A2.4.1 EDR Deploy | T2.4.1.1 Agent deployment | Endpoint Team | M15 | M24 | 9 months | - | Planned |
|  |  | T2.4.1.2 Policy tuning | Security Team | M20 | M30 | 10 months | T2.4.1.1 | Planned |
| M2.5 Network | A2.5.1 Firewalls | T2.5.1.1 Procurement | Procurement | M13 | M16 | 3 months | - | Planned |
|  |  | T2.5.1.2 Deployment (8 sites) | Network Team | M16 | M24 | 8 months | T2.5.1.1 | Planned |

## Phase 3: Education & Research (Years 2-4) - ₹18 Crores

| Module (#) | Activity (#) | Sub-Task (#) | Assignee(s) | Start Date | End Date | Duration | Dependencies | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M3.1 B.Tech | A3.1.1 Program Dev | T3.1.1.1 Curriculum design | Academic Team | M13 | M18 | 5 months | - | Planned |
|  |  | T3.1.1.2 UGC approval | Registrar | M18 | M24 | 6 months | T3.1.1.1 | Planned |
|  | A3.1.2 First Batch | T3.1.2.1 Admissions | Admissions | M20 | M24 | 4 months | T3.1.1.2 | Planned |
|  |  | T3.1.2.2 Program launch | Dean | M24 | M24 | 1 month | T3.1.2.1 | Planned |
| M3.2 Faculty | A3.2.1 Recruitment | T3.2.1.1 Job postings | HR Team | M15 | M18 | 3 months | - | Planned |
|  |  | T3.2.1.2 Hire 20+ faculty | Hiring Committee | M18 | M36 | 18 months | T3.2.1.1 | Planned |
| M3.3 Labs | A3.3.1 Facility | T3.3.1.1 Construction (5K sqft) | Facilities | M18 | M30 | 12 months | - | Planned |
|  |  | T3.3.1.2 Equipment setup | Lab Manager | M28 | M36 | 8 months | T3.3.1.1 | Planned |
|  | A3.3.2 Virtual Labs | T3.3.2.1 Platform setup | IT Team | M20 | M24 | 4 months | - | Planned |
|  |  | T3.3.2.2 100+ tools config | Lab Team | M24 | M36 | 12 months | T3.3.2.1 | Planned |
| M3.4 Research | A3.4.1 Center Setup | T3.4.1.1 Infrastructure | Research Director | M24 | M36 | 12 months | - | Planned |
|  |  | T3.4.1.2 First projects | Faculty | M30 | M36 | 6 months | T3.4.1.1 | Planned |
|  | A3.4.2 Publications | T3.4.2.1 First papers | Researchers | M36 | M48 | 12 months | T3.4.1.2 | Planned |
| M3.5 Certifications | A3.5.1 CEH Program | T3.5.1.1 Material prep | Training Team | M20 | M24 | 4 months | - | Planned |
|  |  | T3.5.1.2 First cohort | Instructors | M24 | M28 | 4 months | T3.5.1.1 | Planned |

## Phase 4: Ecosystem & Partnerships (Years 3-5) - ₹10 Crores

| Module (#) | Activity (#) | Sub-Task (#) | Assignee(s) | Start Date | End Date | Duration | Dependencies | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M4.1 Industry | A4.1.1 Partnerships | T4.1.1.1 Partner identification | Partnership Mgr | M24 | M30 | 6 months | - | Planned |
|  |  | T4.1.1.2 MOUs (20+) | Legal Team | M30 | M48 | 18 months | T4.1.1.1 | Planned |
|  | A4.1.2 Internships | T4.1.2.1 Portal setup | IT Team | M30 | M36 | 6 months | - | Planned |
|  |  | T4.1.2.2 First placements | Placement Team | M36 | M40 | 4 months | T4.1.2.1 | Planned |
| M4.2 Government | A4.2.1 CERT-In | T4.2.1.1 Collab agreement | CISO | M30 | M36 | 6 months | - | Planned |
|  |  | T4.2.1.2 Threat intel sharing | SOC Team | M36 | M72 | Ongoing | T4.2.1.1 | Planned |
|  | A4.2.2 DRDO/ISRO | T4.2.2.1 Research projects | Research Director | M36 | M60 | 24 months | - | Planned |
| M4.3 Universities | A4.3.1 Collaboration | T4.3.1.1 IIT/NIT partnerships | Dean | M36 | M48 | 12 months | - | Planned |
|  | A4.3.2 CTF Comp | T4.3.2.1 First competition | Faculty | M40 | M42 | 2 months | - | Planned |
|  |  | T4.3.2.2 Annual events | Event Team | M48 | M72 | Annual | T4.3.2.1 | Planned |

## Phase 5: Advanced Capabilities (Years 4-6) - ₹10 Crores

| Module (#) | Activity (#) | Sub-Task (#) | Assignee(s) | Start Date | End Date | Duration | Dependencies | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M5.1 Advanced Tech | A5.1.1 Quantum Crypto | T5.1.1.1 Pilot project | Research Team | M48 | M60 | 12 months | - | Planned |
|  | A5.1.2 AI Security | T5.1.2.1 AI threat detection | AI Team | M48 | M72 | 24 months | - | Planned |
|  | A5.1.3 Automation | T5.1.3.1 SOAR platform | SOC Team | M48 | M60 | 12 months | - | Planned |
| M5.2 Privacy | A5.2.1 DPDP Compliance | T5.2.1.1 Privacy framework | Privacy Officer | M42 | M54 | 12 months | - | Planned |
|  | A5.2.2 Data Portal | T5.2.2.1 Student portal | Dev Team | M48 | M60 | 12 months | - | Planned |
| M5.3 Certification | A5.3.1 ISO 27001 | T5.3.1.1 Gap analysis | ISO Consultant | M36 | M42 | 6 months | - | Planned |
|  |  | T5.3.1.2 Remediation | Security Team | M42 | M48 | 6 months | T5.3.1.1 | Planned |
|  |  | T5.3.1.3 Certification audit | Auditor | M48 | M50 | 2 months | T5.3.1.2 | Planned |
| M5.4 Maturity | A5.4.1 Optimization | T5.4.1.1 Process improvement | All Teams | M48 | M72 | 24 months | - | Planned |
|  | A5.4.2 Sustainability | T5.4.2.1 Revenue programs | Business Team | M54 | M72 | 18 months | - | Planned |

# RACI Matrix - Key Stakeholders

RACI: Responsible (R), Accountable (A), Consulted (C), Informed (I)

| Activity | CISO | Exec Director | Moonshot Council | Dean | Faculty | IT Team | Students |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Leadership Setup | R | A | C | C | I | I | I |
| Security Audit | A | C | I | C | I | R | I |
| Policy Development | A | C | C | R | C | C | I |
| SOC Operations | A | I | I | I | I | R | I |
| B.Tech Program | C | C | A | A | R | C | I |
| Research Center | C | C | C | A | R | C | C |
| Lab Setup | C | C | I | A | C | R | I |
| Partnerships | R | A | C | C | C | I | I |
| ISO 27001 Cert | A | C | I | I | I | R | I |
| Training Programs | C | I | I | C | R | C | I |

# Risk Identification

The team used multiple approaches for comprehensive risk identification:

Structured Brainstorming with Moonshot Council and stakeholders

Checklist based on similar cybersecurity transformation projects

Lessons learned from peer institutions (IITs, NITs, international universities)

Assumption-Constraint analysis from project planning phase

SWOT Analysis (Strengths, Weaknesses, Opportunities, Threats)

Expert consultation with CERT-In and cybersecurity industry leaders

Review of cybersecurity incident reports and industry trends

## Risk Categories

Technical Risks: Technology implementation, integration, performance

Resource Risks: Budget, staffing, skills availability

Organizational Risks: Change management, resistance, politics

External Risks: Vendor dependencies, regulatory changes, market conditions

Security Risks: Cyber threats, data breaches, system vulnerabilities

Academic Risks: Accreditation, student enrollment, faculty quality

Timeline Risks: Schedule delays, dependency conflicts

Financial Risks: Cost overruns, ROI concerns, funding availability

# Risk Register - List and Describe

Comprehensive register of identified risks with potential impacts:

| Risk ID | Risk Description | Impact Description |
| --- | --- | --- |
| R-001 | Difficulty recruiting qualified CISO within 3 months | Delays in program kickoff, leadership vacuum, affects all downstream activities |
| R-002 | Budget overruns exceeding ₹75 crore allocation | Scope reduction, program delays, quality compromises, stakeholder confidence loss |
| R-003 | Cannot recruit 50+ cybersecurity professionals | Understaffed teams, burnout, quality issues, timeline delays, vendor dependencies |
| R-004 | SIEM platform vendor selection conflicts | 6-month delay in SOC operations, team disagreements, suboptimal tool choice |
| R-005 | Legacy system incompatibility with Zero Trust | Costly infrastructure upgrades, timeline delays, security gaps, user frustration |
| R-006 | Faculty and staff resistance to MFA and policies | Low adoption, security gaps, user workarounds, training burden |
| R-007 | Insufficient student enrollment (< 60 B.Tech Y2) | Revenue shortfall, program viability questioned, faculty underutilization |
| R-008 | UGC delays in B.Tech program approval | 6-12 month delay in program launch, lost cohort, competitive disadvantage |
| R-009 | Industry partners fail to provide internships | Poor placement rates, student dissatisfaction, reputation damage |
| R-010 | DPDP Act compliance requirements unclear | Non-compliance risks, legal exposure, implementation delays, rework |
| R-011 | Cloud service provider outages | System downtime, data access issues, business continuity risks |
| R-012 | Cyber attack during implementation phase | Data breach, reputation damage, project credibility loss, regulatory issues |
| R-013 | Key personnel turnover (CISO, directors) | Knowledge loss, momentum loss, timeline delays, morale impact |
| R-014 | Research funding targets not met (₹10Cr/year) | Research center viability, faculty retention issues, competitive disadvantage |
| R-015 | ISO 27001 certification audit failure | Credibility loss, remediation costs, timeline extension, stakeholder concerns |
| R-016 | Internet bandwidth insufficient at some campuses | Cloud tool performance issues, user frustration, training disruptions |
| R-017 | Vendor lock-in with critical security tools | High ongoing costs, limited flexibility, dependency risks |
| R-018 | Competition from IITs/NITs launches similar programs | Student diversion, faculty poaching, market saturation |
| R-019 | Lab equipment procurement delays | Hands-on training compromised, student dissatisfaction, curriculum gaps |
| R-020 | SOC 24x7 staffing burnout | High turnover, quality degradation, incident response delays |
| R-021 | Threat intelligence feed quality issues | False positives/negatives, SOC efficiency drop, missed threats |
| R-022 | Data center power/cooling capacity limits | Infrastructure expansion blocked, scalability issues, performance degradation |
| R-023 | Privacy concerns from enhanced monitoring | Legal challenges, user backlash, policy conflicts, trust erosion |
| R-024 | Endpoint EDR agent conflicts with software | User productivity loss, help desk overload, workaround requests |
| R-025 | Phishing simulation causes real alert fatigue | Reduced vigilance, training effectiveness questioned, user complaints |
| R-026 | Research output quality below expectations | Funding loss, faculty recruitment issues, ranking impact |
| R-027 | Certification exam pass rates low (< 70%) | Program credibility questioned, student dissatisfaction, curriculum review |
| R-028 | Partnership MOUs fail to materialize benefits | Placement gaps, research collaboration missing, resource waste |
| R-029 | CERT-In threat intelligence sharing delays | Reduced threat visibility, incident response gaps, isolation risk |
| R-030 | Disaster recovery plan inadequate | Extended outages, data loss, business continuity failure |
| R-031 | Compliance reporting automation failures | Manual effort overload, audit risks, reporting delays |
| R-032 | Student data privacy breach incident | Legal liability, reputation damage, regulatory penalties, trust loss |
| R-033 | Advanced tech (quantum crypto) not mature | Research dead ends, resource waste, competitive parity |
| R-034 | Revenue generation targets not achieved | Sustainability concerns, dependency on university funding |
| R-035 | Geographic campus distribution coordination | Communication gaps, inconsistent implementation, quality variance |

# Managing Risk

Risks categorized by severity and likelihood with defined mitigation actions:

| Risk ID | Status | Risk Appetite | Action | Action Owner | Timeline | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | Open | Mitigate | Use executive search firm, competitive comp package | HR Director | M1-M3 | ₹10L |
| R-002 | Open | Mitigate | Phased budget with go/no-go gates, contingency fund (10%) | CFO | Ongoing | ₹7.5Cr |
| R-003 | Open | Mitigate | Partner with staffing firms, competitive salaries, train internal | CISO/HR | Ongoing | ₹2Cr |
| R-004 | Open | Accept | Form vendor selection committee, POC testing, vendor demos | CISO | M8-M10 | ₹50L |
| R-005 | Open | Mitigate | Phased Zero Trust rollout, legacy system upgrades planned | Network Lead | M18-M48 | ₹3Cr |
| R-006 | Open | Mitigate | Extensive training, change management, executive sponsorship | Change Mgr | M6-M18 | ₹80L |
| R-007 | Open | Mitigate | Marketing campaign, scholarship programs, campus outreach | Admissions | M18-M24 | ₹1Cr |
| R-008 | Open | Accept | Early UGC engagement, complete documentation, follow-up | Registrar | M18-M24 | ₹20L |
| R-009 | Open | Mitigate | 20+ partnerships, guaranteed internship MOUs, tracking system | Partnership Mgr | M24-M48 | ₹50L |
| R-010 | Open | Accept | Legal counsel, industry association membership, flexibility | Legal/Privacy | M6-M36 | ₹30L |
| R-011 | Open | Transfer | Multi-cloud strategy, SLA with penalties, backup systems | IT Director | M13-M18 | ₹1Cr |
| R-012 | Open | Mitigate | Enhanced monitoring, IR plan, cyber insurance, backup/DR | CISO | Ongoing | ₹2Cr |
| R-013 | Open | Mitigate | Competitive retention packages, succession planning, cross-training | HR/Exec Dir | Ongoing | ₹1.5Cr |
| R-014 | Open | Mitigate | Diversified funding sources, strong proposal team, faculty incentives | Research Dir | M24-M72 | ₹80L |
| R-015 | Open | Avoid | Early gap analysis, consultant support, mock audits, remediation time | ISO Lead | M36-M50 | ₹60L |
| R-016 | Open | Mitigate | Bandwidth upgrades, prioritization, hybrid cloud/on-prem | IT Ops | M6-M24 | ₹1.5Cr |
| R-017 | Open | Accept | Vendor-agnostic architecture, open standards, contract negotiation | CISO | M8-M12 | ₹30L |
| R-018 | Open | Accept | Unique value proposition, partnerships, hands-on focus, rapid launch | Exec Dir | M18-M36 | ₹70L |
| R-019 | Open | Mitigate | Early procurement, multiple vendors, phased delivery, rental options | Lab Manager | M18-M36 | ₹2Cr |
| R-020 | Open | Mitigate | Adequate staffing (15+), rotation schedules, wellness programs | SOC Manager | M18-M72 | ₹1.2Cr |
| R-021 | Open | Mitigate | Multiple feed sources, validation process, analyst training | Threat Lead | M18-M24 | ₹40L |
| R-022 | Open | Accept | Data center assessment, upgrade plan, cloud expansion option | Facilities | M13-M18 | ₹1Cr |
| R-023 | Open | Mitigate | Privacy policy framework, transparency, privacy officer role | Privacy Officer | M6-M36 | ₹50L |
| R-024 | Open | Accept | Thorough testing, exemption process, help desk expansion | Endpoint Team | M15-M24 | ₹40L |
| R-025 | Open | Accept | Balanced frequency, clear communication, feedback mechanisms | Training Team | M8-M72 | ₹20L |
| R-026 | Open | Mitigate | Quality faculty hiring, mentorship, peer review, funding support | Research Dir | M24-M72 | ₹1Cr |
| R-027 | Open | Mitigate | Quality instructors, adequate prep time, practice exams, tutoring | Training Lead | M24-M72 | ₹60L |
| R-028 | Open | Mitigate | Structured partnership agreements, KPIs, regular reviews | Partnership Mgr | M30-M60 | ₹30L |
| R-029 | Open | Accept | Direct CERT-In engagement, backup intel sources, industry forums | CISO | M30-M36 | ₹20L |
| R-030 | Open | Mitigate | Comprehensive DR plan, testing, geo-redundancy, documentation | IT Ops | M13-M24 | ₹1.5Cr |
| R-031 | Open | Mitigate | Robust automation, testing, manual backup procedures | Compliance Team | M24-M36 | ₹40L |
| R-032 | Open | Avoid | Enhanced controls, encryption, access controls, IR plan, insurance | CISO/Privacy | Ongoing | ₹80L |
| R-033 | Open | Accept | Pilot approach, academic focus, partnerships, flexible timeline | Research Dir | M48-M72 | ₹50L |
| R-034 | Open | Mitigate | Diversified revenue, business development, quality programs | Business Team | M54-M72 | ₹60L |
| R-035 | Open | Accept | Video conferencing, travel budget, campus coordinators, unified tools | Exec Dir | Ongoing | ₹80L |

# Risk Priority Matrix

Risks categorized by Probability and Impact:

| Probability \ Impact | Low | Medium | High | Critical |
| --- | --- | --- | --- | --- |
| Very High (80%+) |  | R-006 | R-003, R-007 | R-002, R-012 |
| High (60-80%) |  | R-016, R-024 | R-001, R-005, R-013 | R-032 |
| Medium (40-60%) | R-025 | R-008, R-018, R-027 | R-004, R-009, R-015 |  |
| Low (20-40%) | R-010, R-029 | R-014, R-019, R-022 | R-011, R-030 |  |
| Very Low (<20%) | R-017, R-033 | R-021, R-026, R-034 |  |  |

**Critical Priority Risks (Immediate Action Required):** R-002, R-012, R-032

**High Priority Risks (Close Monitoring):** R-001, R-003, R-005, R-007, R-013

**Medium Priority Risks (Standard Mitigation):** R-004, R-006, R-008, R-009, R-015, R-016, R-018, R-024, R-027

# Contingency Plans for Critical Risks

## R-002: Budget Overruns

**Trigger:** Budget variance exceeds 10% (₹7.5 crores) in any phase

**Contingency Actions:**
1. Activate contingency fund (10% of total budget = ₹7.5 crores)
2. Convene emergency Moonshot Council meeting for scope review
3. Prioritize critical security infrastructure over nice-to-have features
4. Seek additional funding from industry partnerships or government grants
5. Extend timeline for non-critical components to next phase
6. Consider phased hiring instead of bulk recruitment

**Decision Authority:** CFO and Moonshot Council
**Escalation Path:** Vice Chancellor → Board of Trustees

## R-012: Cyber Attack During Implementation

**Trigger:** Successful cyber attack causing data breach or significant disruption

**Contingency Actions:**
1. Activate Incident Response Plan immediately
2. Isolate affected systems within 15 minutes
3. Notify CERT-In within 6 hours per regulations
4. Engage cyber insurance provider and forensics team
5. Implement emergency communication plan to stakeholders
6. Execute disaster recovery procedures
7. Conduct post-incident review and implement lessons learned
8. Accelerate security controls deployment

**Decision Authority:** CISO
**Escalation Path:** Vice Chancellor → Legal → Public Relations

## R-032: Student Data Privacy Breach

**Trigger:** Unauthorized access or disclosure of student personal data

**Contingency Actions:**
1. Activate data breach response plan within 1 hour
2. Contain breach and assess scope immediately
3. Notify affected students within 72 hours per DPDP Act
4. Report to Data Protection Authority as required
5. Offer credit monitoring or identity protection services
6. Engage legal counsel and PR firm
7. Implement immediate security enhancements
8. Conduct forensic investigation
9. Review and strengthen all privacy controls
10. Consider cyber insurance claim

**Decision Authority:** CISO and Privacy Officer
**Escalation Path:** Vice Chancellor → Legal → Regulatory Authority

# Risk Monitoring and Control

**Monthly Risk Reviews:**
• Risk register review by CISO and Executive Director
• Status updates for all open risks
• New risk identification from ongoing activities
• Mitigation action effectiveness assessment

**Quarterly Risk Reports:**
• Comprehensive risk status report to Moonshot Council
• Risk trend analysis and emerging threats
• Budget impact of risk mitigation activities
• Escalation of critical risks requiring Council action

**Annual Risk Assessment:**
• Complete re-evaluation of all risks
• Update risk probabilities and impacts
• Validate mitigation strategies effectiveness
• Incorporate lessons learned from incident history

**Key Risk Indicators (KRIs):**
• Budget variance percentage (Target: < 5%)
• Timeline slippage (Target: < 10% per phase)
• Staff turnover rate (Target: < 15% annually)
• Security incident count (Target: Zero major breaches)
• Student enrollment vs. targets (Target: ≥ 90%)
• Research funding secured (Target: ₹10+ crores/year)
• Partnership engagement (Target: 20+ active MOUs)
• Certification pass rates (Target: ≥ 75%)

**Risk Communication:**
• Monthly risk dashboard for leadership
• Quarterly risk briefings to Moonshot Council
• Real-time critical risk escalation protocols
• Annual risk report to Board of Trustees

# Reference

1. Project Management Institute (PMI) - https://www.pmi.org/

2. PMBOK Guide - Project Management Body of Knowledge

3. ISO 31000:2018 - Risk Management Guidelines

4. NIST SP 800-30 - Guide for Conducting Risk Assessments

5. COBIT 2019 - Risk Management Framework

6. FAIR Risk Management - Factor Analysis of Information Risk

7. COSO ERM Framework - Enterprise Risk Management

8. Lessons Learned from IIT Cybersecurity Programs

9. CERT-In Risk Management Best Practices

10. Higher Education Cybersecurity Implementation Guide

# Document Approval

_____________________________________________

Chief Information Security Officer (CISO)

Date: _______________

_____________________________________________

Executive Director - Moonshot Initiative

Date: _______________

_____________________________________________

Vice-Chancellor, SRM University

Date: _______________